## Sheet1
Risk Assessment Plan
Citation: Risk Management Guide for DOD 2006 Acquisition http://www.dau.mil/pubs/gdbks/docs/RMG%206Ed%20Aug06.pdf

Risk Title	Causal Factor	Likelihood	Impact	Mitigation Plan
Team collboration	Team members are distanced from one another	5	3	Use three-way video conferencing to enable virtual face-to-face collaboration at least weekly. Use software version control to help merge branches.
Architecture fails to support product	Little time for technology exploration	2	5	Leave time for emergency redesign effort. Identify an additional, diverse technology candidate in case our first choice doesn't work out
Schedule	Team could not finish target implementation by deadline	2	5	Scope a practical amount of work for the target implementation and delegate outstanding items to the dream implementation.
No common development envrionment	Team members all have different configurations on development machines	5	2	Whenever possible, use Free and Open Source Software tools which are designed for cross platform use.
Computer network availability	Distanced team members rely 100% on connectivity	1	5	Frequest commits to distributed version control system in case team members go offline for any significant amount of time
Team Health	Flu season is coming	4	3	Team members can seek flu shots and maintain their health as best of possible. Finish planned work early to reduce stress.