## Sheet1
Risk Assessment Plan
Citation: Risk Management Guide for DOD 2006 Acquisition http://www.dau.mil/pubs/gdbks/docs/RMG%206Ed%20Aug06.pdf
Risk Title | Causal Factor | Likelihood | Impact | Mitigation Plan
Team collboration | Team members are distanced from one another | 5 | 3 | Use three-way video conferencing to enable virtual face-to-face collaboration at least weekly. Use software version control to help merge branches.
Architecture fails to support product | Little time for technology exploration | 2 | 5 | Leave time for emergency redesign effort. Identify an additional, diverse technology candidate in case our first choice doesn't work out
Schedule | Team could not finish target implementation by deadline | 2 | 5 | Scope a practical amount of work for the target implementation and delegate outstanding items to the dream implementation.
No common development envrionment | Team members all have different configurations on development machines | 5 | 2 | Whenever possible, use Free and Open Source Software tools which are designed for cross platform use.
Computer network availability | Distanced team members rely 100% on connectivity | 1 | 5 | Frequest commits to distributed version control system in case team members go offline for any significant amount of time
Team Health | Flu season is coming | 4 | 3 | Team members can seek flu shots and maintain their health as best of possible. Finish planned work early to reduce stress.